## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name | Tool mania |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Barry Hiku
Project Start Date: | 2026-02-22 |  |  |  |  | February | [6 empty] | March | [34 empty] | April
Scrolling Increment: | 1 |  |  |  |  | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Project definition
Site naming | Low risk | Group collaberation | 25% | 2026-04-30 | 3 | bar: M to W
Project planning | High risk | Group collaberation |  | 2026-02-28 | 5 | bar: S to W
Project confirmation | Low risk | Barry Hiku | 50% | 2026-03-07 | 1 | bar: S
Content phase
Ideation phase | Medium | Jaris Hema-Taylor | 60% | 2026-03-08 | 4 | bar: S to W
Design principle | High risk | Jaris Hema-Taylor | 50% | 2026-03-08 | 5 | bar: S to W
Content confirmation | Low Risk | Barry Hiku | 33% | 2026-03-14 | 11
Design phase
Wireframe | On Track | Barry Hiku/ Anthony Start |  | 2026-03-20 | 6 | bar: F to T
Mockup | Med Risk | Barry Hiku/ Anthony Start |  |  | 3 | bar: S to M
Prototype | On Track | Barry Hiku/ Anthony Start |  | 2026-03-31 | 3 | bar: T to T
Task 5 | Low Risk |  |  |  | 19
Development phase
Peusodocoding/flowcharting |  |  |  | 2026-04-05 | 4 | bar: S to W
Website coding |  |  |  | 2026-04-09 | 3 | bar: T to S
Test | Milestone | Jaris Hema-Taylor |  | 2026-04-12 | 3 | bar: S to T
Rework |  |  |  | 2026-04-17 | 2 | bar: W to T
Review phase
Project review |  | Anothonty stark |  | 2026-04-17 | 1 | bar: F
Deployment |  | Team collaberation |  | 2026-04-18 | 2

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2026-04-22 |  |  |  |  | April | [13 empty] | May | [27 empty] | June
Scrolling Increment: | 1 |  |  |  |  | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2026-04-29 | 3 | W: 2; T: 2; F: 2
Task 2 | Milestone |  |  | 2026-05-04 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2026-04-26 | 10
Task 4 | Milestone |  |  | 2026-05-19 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2026-05-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-05-05 | 13
Task 2 | On Track |  | 50% | 2026-05-07 | 9
Task 3 | Low Risk |  | 33% | 2026-05-12 | 11
Task 4 | Milestone |  |  | 2026-05-14 | 1 | bar: T
Task 5 |  |  |  | 2026-05-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-05-14 | 4
Task 2 | Med Risk |  |  | 2026-05-17 | 14
Task 3 | On Track |  |  | 2026-06-01 | 6
Task 4 | Goal |  |  | 2026-06-05 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2026-05-05 | 19
TITLE 4
Task 1 |  |  |  | 2026-06-08 | 15
Task 2 |  |  |  | 2026-06-22 | 5
Task 3 | Milestone |  |  | 2026-08-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2026-04-22 |  |  |  |  | April | [6 empty] | May | [27 empty] | June
Scrolling Increment: | 5 |  |  |  |  | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TITLE 1
Task 1 | Goal | Name | 25% | 2026-04-29 | 3 | W: 2; T: 2; F: 2
Task 2 | Milestone |  |  | 2026-05-04 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2026-04-26 | 10
Task 4 | Milestone |  |  | 2026-05-19 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2026-05-05 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2026-05-05 | 13
Task 2 | On Track |  | 50% | 2026-05-07 | 9
Task 3 | Low Risk |  | 33% | 2026-05-12 | 11
Task 4 | Milestone |  |  | 2026-05-14 | 1 | bar: T
Task 5 |  |  |  | 2026-05-15 | 24
TITLE 3
Task 1 | On Track |  |  | 2026-05-14 | 4
Task 2 | Med Risk |  |  | 2026-05-17 | 14
Task 3 | On Track |  |  | 2026-06-01 | 6
Task 4 | Goal |  |  | 2026-06-05 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2026-05-05 | 19
TITLE 4
Task 1 |  |  |  | 2026-06-08 | 15
Task 2 |  |  |  | 2026-06-22 | 5
Task 3 | Milestone |  |  | 2026-08-03 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one