## Sheet1
Deliverables: |  | Resources required: | Time required (hrs) | Amount of Resources required: | Cost:
Task: | Description:
1 | Planning Phase | members / meeting / laptop | 1 | 1 | 1160
1.1 |  | members / meeting / laptop | 0.5 | 0 | 30
[6 empty] | Resource: | Cost:
1.2 | assigning titles | members / meeting / laptop | 0.5 | 0 | 30 | Laptop | 1100
[6 empty] | Software Eng. | 60
1.3 | market research | members / laptop | 6 | 4 | 4760
1.4 | Initial Website Design | laptop | 27 | 4 | 1620
2 | Prototype Development | members / laptop | 336 | 2 | 20160
2.1 | Testing | members / laptop | 72 | 1 | 4320
2.2 | Prototype Rework | members / laptop | 168 | 2 | 10080
2.3 | Final Testing | members / laptop | 96 | 1 | 5760
2.4 | Finished Build | members / laptop | 168 | 2 | 10080
3 | Demonstration | members / laptop | 4 | 1 | 240
3.1 | Closing | members | 12 | 0 | 720
0
Total: |  |  | 909 | 18 | 58960